## Sheet1
Bug ID | 1
Bug Title | Frontal Area allows string value
Bug Description | When WLTP relevancy value is Yes for WLTP, user need to input "Frontal Area" with integer value. Frontal Area field is string data type.
Steps to replicate | 1. Login in to the application
2. Go to WTLP data from left navigation menu or click WTLP data on dashboard
3. Add or Edit WTLP data by clicking on 'Create WLTP Data' button or by clicking on existing WTLP data from list respectively
4. Enter all required field values
5. Select Yes for WLTP relevancy value
6. User should be able to enter "Frontal Area" value
7. Enter "STRONG" (or any String value) into the "Frontal Area" field
8. Save WTLP data
Expected Result | The "Frontal Area" should be stored as an integer
Actual Result | User was able to save WTLP data with Frontal Area with string value
Severity | High
Priority | Medium
Environment | Staging
Reported by | Silu Pandit
Reported on | 2023-07-24
Status | New
Assigned To | Dev Lead
Bug ID | 2
Bug Title | MasterCode exceeded 3 characters limit.
Bug Description | When creating new product MasterCode field should only have 3 characters.
Steps to replicate | 1. Login in to the application
2. Go to Product from left navigation menu or click Product on dashboard
3. Add or Edit Product by clicking on 'Create Product' button or by clicking on existing product from list respectively
4. Enter all required field values
5. Enter MasterCode with more than 3 characters
Expected Result | MasterCode field should not exceed 3 characters limit.
Actual Result | MasterCode exceeded 3 characters limit.
Severity | Medium
Priority | High
Environment | Staging
Reported by | Silu Pandit
Reported on | 2023-07-24
Status | New
Assigned To | Dev Lead